## Slide 1: Action4Diabetes
Monthly Update December

## Slide 2: Today‘s Topics
Project overview
Data consistency
Database deep dive (& feedback)
Lessons learned for Laos data

## Slide 3: Project Overview
1. Setup project infrastructure | 2. Ensure encrypted database hosting | 3. Data cleaning pipelines | 4. Database schema | 5. Data ingestion | 6. Iterative Analysis & Visualisation | 7. Quality Assurance | 8. Handover
100% | 100% | 90% | 100% | 10% | 0% | 0% | 0%
Done last month | Upcoming this month
Preparation for data ingestion Validation pseudonymized data | Data Ingestion

## Slide 4: Data consistency
Make sure that all tabs within a workbook are the same
  Product section
  Patient data existing
  Sheets within a workbook have the same columns

## Slide 5: Database Deep Dive
What are we doing?
Why?
Centralizing historical patient data in a database
Facilitate data handling & releases
Set up structure for future operationalization
Create basis for exploratory data analysis
Overview

## Slide 6: Database Deep Dive
Static patient data
Course of patient‘s treatment (visits)
Medication supply
Date of birth
Benchmarks
…
When & where was last visit?
Latest HbA1c/Fbg values
…
Supply received in clinics
Supply handed out to patients
…
Data Dimensions

## Slide 7: Database Deep Dive
Data Processing
Excel sheets
Collect & clean data
Raw, cleaned data
Aggregate information
Processed data
Align & upload to database
Structured data in database

## Slide 8: Database Deep Dive
Simplified Database Structure - Tables
Patients
Clinics
Products
Visits
Given products
Who are our patients?
Which clinics do we support?
When do patients visit the clinic?
What has changed?
Which products are in use?
Which products were given out?

## Slide 9: Database Deep Dive
Simplified Database Structure – Visit Relations
Patients
Clinics
Products
Visits
Given products
Who?
Where?

## Slide 10: Database Deep Dive
Simplified Database Structure – Released Products Relation
Patients
Clinics
Products
Visits
Given products
Who?
Where?
What?

## Slide 12: Database Deep Dive
Current Status
Excel sheets
Collect & clean data
Raw, cleaned data
Aggregate information
Processed data
Align & upload to database
Finalize data pipelines with new input
Map finalized information to database structure
Structured data in database
Structure created (in SQL) – needs to be filled
Applied existing pipelines to new data

## Slide 13: Questions & Feedback
?…!